## Start Here
Topic | Explanation
Purpose | Entroid FP&A Phase 4: stakeholder-ready future-state change register
Date | 2026-10-29
Sources | F&P SS.pdf (27 pages); Untitled spreadsheet - Sheet1.csv (83 feature rows)
Scope | Planning & Budgeting screenshot subset; 83-row wider FP&A capability catalogue
Agreed navigation | Workflow-first; role-based and permission-scoped
Agreed advanced features | Optional/configurable; not core-MVP blockers
Agreed development priority | Complete core budgeting lifecycle first
Evidence distinction | Screenshot-visible does not prove executable function; user confirms there is no backend
P0 | Core MVP; High priority
P1 | Next expansion; Medium priority
P2 | Advanced/optional; Low priority
Client-mandated status | No requirements identified as contractually mandated; Y/N ignored as instructed
Wave note | P0 denotes a usable scoped subset when catalogue language describes more advanced capabilities; see MVP Coverage / Scope Caveat
Requirement IDs | R001–R083 correspond in original CSV order; used in screen matrix for traceability
PDF pagination | Pages 22 and 25 are section dividers, not application screens
Limitation | Other Entroid Revenue, Cost, Forecasting, Reporting and Setup screens not reviewed here
Action code | Keep + Modify / Modify / Merge / Split + Modify / Relocate / Add / Add + Link
Working assumption | Source screenshot PDF includes several views per page; matrix is at visible screen/view level
Approval note | This register is a recommendation set pending stakeholder sign-off, not an implemented specification

## Screen Change Matrix
ID | Existing Module | Screen / View | PDF page(s) | Current Purpose (visible) | Recommended Action | Proposed Change | Business Rationale | Priority | Delivery Wave | Requirement IDs | Change Classification | Evidence Status | Validation / Open Rule | Proposed Location | Primary Persona
S01 | Long-Range Plan | Five-year plan overview | 1 | KPI cards and FY2026–2030 projection table | Relocate | Preserve multi-year plan overview under Strategic Planning; connect to planning assumptions and annual-cycle target bridge. | Strategic planning is valid but should not interrupt annual budget entry. | Medium | P2 | R006,R063,R065,R070 | Generic product | Visible | Define forecast source, financial statement calculations | Strategic Planning | FP&A Manager
S02 | Long-Range Plan | Projection account and hierarchy selectors | 2 | Account/hierarchy filters and projected line-item table | Modify | Use common account/dimension selectors and drill-down standards across planning models. | Prevents mismatched financial dimensions and account taxonomy. | Medium | P2 | R001,R002,R003,R074 | Generic product | Visible | Check actual dimension dropdown options | Strategic Planning | FP&A Analyst
S03 | Long-Range Plan | Assumptions and planning drivers | 2 | Assumption-driver table and approval indicator | Merge | Use central assumptions library with scenario and version tracking; retain LRP-specific override views. | Shared assumptions avoid inconsistent growth/FX inputs. | Medium | P2 | R019,R048,R005 | Generic product | Visible | Confirm override precedence and audit policy | Assumptions (shared) | FP&A Manager
S04 | Long-Range Plan | Charts, version and gap views | 3–4 | Financial KPI charts, version audit, plan-to-AOP gap/bridge | Modify | Connect charts and AOP gap measures to published plan versions with clear variance sign conventions. | Makes strategy-to-budget comparison reproducible. | Medium | P2 | R005,R063,R067,R078 | Generic product | Visible | Define bridge formula and sign convention | Strategic Planning | FP&A Manager
S05 | Budget Targets | Targets overview and draft/approved selector | 4 | Financial target cards, target list, draft/approved view | Modify | Show targets in a budget cycle with explicit scope, owners, effective version and allocation progress. | Targets must be actionable within same annual plan. | High | P0 | R014,R015,R066 | Generic product | Visible | Clarify role of draft versus approved selector | Budget Planning > Targets | FP&A Manager
S06 | Budget Targets | New target form | 5 | Category, dimension, dimension value, input method, amount, prior actual, notes | Modify | Validate account category, dimension scope, input method, prior actual source, currency and target period; show effect preview. | Prevents invalid targets and unexplained baseline values. | High | P0 | R002,R003,R015,R066 | Generic product | Visible | Confirm input method choices and period granularity | Budget Planning > Targets | FP&A Manager
S07 | Budget Targets | Cost-centre allocation | 6 | Cost-centre allocation rows and target figures | Modify | Allocate top-down target into departmental ceilings; track allocated/unallocated balance and prevent over-allocation. | Makes target cascading auditable and usable. | High | P0 | R015,R016,R059,R066 | Generic product | Visible | Agree allocation methods and rounding | Budget Planning > Targets | FP&A Manager
S08 | Budget Targets | Target approval workflow | 6 | CFO/CEO/Board approval-stage controls | Merge | Use central approval engine with a target-specific policy; show embedded approval tab in targets. | Prevents multiple independent approval implementations. | High | P0 | R008,R009,R069,R078 | Generic product | Visible | Authority threshold and board approval rules | Budget Planning > Targets / My Approvals | Approver
S09 | Department Budgets | Department selector and status summary | 7 | Department selector, budget KPIs, owner and status | Modify | Open assigned departments inside active budget cycle; include deadline, last edit, target gap and validation state. | Creates clear role-based starting journey. | High | P0 | R014,R016,R021,R069 | Generic product | Visible | Final permission and organisation model | Budget Planning > Cycle > Departments | Budget Owner
S10 | Department Budgets | Monthly budget entry grid | 7 | Account line-items with monthly amounts and totals | Keep + Modify | Support typed cells, formula totals, row-level validation, save draft, change markers, currency/period policies and bulk paste. | Primary operational screen of annual budget. | High | P0 | R002,R006,R014,R021,R023 | Generic product | Visible | Confirm account roll-ups and writeback policy | Budget Planning > Cycle > Department Detail | Budget Owner
S11 | Department Budgets | Copy From / Add Line / Submit | 7 | Copy previous actuals/budget/ZBB/template, Add Line and Submit | Modify | Add source-preview and duplicate handling; check missing accounts and target breach before submission; persist submission snapshot. | Makes entry and submission deterministic. | High | P0 | R013,R014,R016,R069 | Generic product | Visible; backend absent | Copy/merge rules, editable account set | Budget Planning > Cycle > Department Detail | Budget Owner
S12 | Zero-Based Budgeting | ZBB dashboard and package list | 8 | Package totals, funding envelope and list | Relocate | Make ZBB an enabled planning methodology inside budget cycle/advanced planning, rather than compulsory top-level navigation. | Valid alternative methodology but not all organisations use it. | Low | P2 | R017,R069 | Generic product | Visible | Determine mixed-method support by department | Advanced Planning > ZBB | FP&A Manager
S13 | Zero-Based Budgeting | Create/edit decision package | 9 | Description, justification, spend, frequency, ranking, OKR, risk and impact | Modify | Require account mapping, time-phased amounts, department owner, evidence and duplicate-reference checks; preserve scoring. | Converts proposals into auditable financial objects. | Low | P2 | R017,R019,R065 | Generic product | Visible | Define package scoring rubric and spending schedule | Advanced Planning > ZBB > Package | Budget Owner
S14 | Zero-Based Budgeting | Prioritisation and funding waterfall | 10 | Package ranking/funding waterfall and prior-year variance | Modify | Show eligible packages and approval funding outcome, then map funded portions into budget lines using controlled posting/linking. | Prevents ZBB numbers existing only in isolated view. | Low | P2 | R017,R060,R069 | Generic product | Visible | Partial funding and double-count policy | Advanced Planning > ZBB | FP&A Manager
S15 | Budget Revision | Revision/reforecast overview and line changes | 11 | Change-log, delta/impact KPIs, baseline and justification | Split + Modify | Separate formal budget amendment screen from forecast cycle; identify approved baseline, revision number, affected lines and business justification. | Forecast must not silently overwrite approved budget. | Medium | P1 | R005,R027,R028,R051,R078 | Generic product | Visible | Formal revision policy and reforecast ownership | Budget Planning > Revisions / Forecasts | FP&A Manager
S16 | Budget Revision | Reforecast summary and variance table | 11–12 | Reforecast comparison, impacted rows and projected change figures | Modify | Calculate absolute/percentage change with zero-denominator safeguards; label forecast versus revised budget distinctly. | Avoids misleading +100% display for zero base and unclear comparison. | Medium | P1 | R029,R050,R051,R071 | Generic product | Visible | Agree favourable/unfavourable and zero-base logic | Forecasts & Scenarios | FP&A Manager
S17 | Budget Revision | Revision approvals and version list | 12 | Budget owner/FP&A/CFO stages and version tabs | Merge | Route formal amendment via shared workflow engine; publish approved new baseline without changing original published version. | Maintains audit and historical comparability. | Medium | P1 | R005,R069,R078 | Generic product | Visible | Define who may initiate revision and threshold approvals | Budget Planning > Revisions | Approver
S18 | Budget Revision | Revision audit trail | 13 | Revision action history and timeline | Merge | Display shared immutable audit events and trace affected budget lines and actor, timestamp, before/after values. | Reduces duplicate history mechanisms. | Medium | P1 | R078,R069 | Generic product | Visible | Retention, access, event-detail policy | Planning Governance > Audit | FP&A Controller
S19 | Contingency Plans | Crisis response overview / triggers | 13 | Trigger states, scenario cards, response progress and scorecards | Relocate | Keep as optional advanced scenario application; link baseline and affected financial drivers. | Specialist stress response should not block routine annual budget. | Low | P2 | R043,R046,R048 | Generic product | Visible | Trigger ownership and activation criteria | Advanced Planning > Contingencies | FP&A Manager
S20 | Contingency Plans | Response actions and impact analysis | 14 | Action register, owners, impacts and projected financial deltas | Modify | Tie actions to scenario assumptions and P&L/BS/CF impact; require decision to publish into live forecast. | Prevents simulated impact being treated as committed plan. | Low | P2 | R043,R044,R046,R070 | Generic product | Visible | Response approval, quantification method | Advanced Planning > Contingencies | CFO
S21 | Contingency Plans | Playbooks, tracking and audit history | 15 | Response playbook, action statuses and history | Merge | Reuse common tasks, comments and audit; retain specialist trigger/playbook data. | Avoids parallel governance implementations. | Low | P2 | R069,R078 | Generic product | Visible | Escalation, owner assignment rules | Advanced Planning > Contingencies | FP&A Manager
S22 | M&A Integration | Deal overview and synergy tracking | 16 | Deal-value KPIs, synergy pipeline, integration cost table | Relocate | Offer as optional M&A financial planning extension with explicit deal/entity scope. | Specialist corporate-development workflow, not required for generic annual budget. | Low | P2 | R004,R037,R063 | Generic product | Visible | Acquisition accounting expectations | Advanced Planning > M&A | Corporate Development
S23 | M&A Integration | Combined P&L and 100-day plan | 17 | Combined financial forecast and integration checklist | Modify | Link synergy items into planned accounts/periods; avoid treating combined P&L as actual consolidation engine. | Financial effects must reconcile to plan and reflect relevant consolidation rules. | Low | P2 | R037,R042,R070 | Generic product | Visible | Consolidation and elimination policy | Advanced Planning > M&A | FP&A Manager
S24 | M&A Integration | Deal details / audit | 18 | Acquisition stage details and audit log | Merge | Reuse common change history/permissions; maintain deal-specific fields and evidence. | Governance consistency for specialist workflows. | Low | P2 | R009,R078 | Generic product | Visible | Entity lifecycle/transactions source | Advanced Planning > M&A | Corporate Development
S25 | Initiative Plans | Initiative list and funding KPIs | 19 | Initiative cards, costs/benefits and status | Relocate | Make initiative planning optional; establish unique initiative ID and linked plan line-items. | Prevents independent totals from double counting in department budgets. | Low | P2 | R004,R040,R041,R063 | Generic product | Visible | Source of benefit estimates | Advanced Planning > Initiatives | Business Sponsor
S26 | Initiative Plans | Department cost allocation and ROI tracking | 20 | Department allocations, planned/actual ROI dashboard | Modify | Reference account and period for every initiative cost/benefit; reconcile initiative summaries to overall budget. | Creates credible cross-functional visibility. | Low | P2 | R040,R042,R063,R067 | Generic product | Visible | Cost allocation owner and ROI calculation method | Advanced Planning > Initiatives | FP&A Manager
S27 | Initiative Plans | Stage gates and audit | 21 | Gate review decisions and activity history | Merge | Reuse shared approval and audit with initiative-stage policy, preserving signoff evidence. | Consistent workflow, fewer fragmented approval implementations. | Low | P2 | R069,R078 | Generic product | Visible | Gate authority, benefit realisation criteria | Advanced Planning > Initiatives | Business Sponsor
S28 | Budget Versions | Version inventory / create / lock | 23 | Version names, status, active flag, owners and actions | Merge + Modify | Make plan-version service shared; explicitly separate name, approval state, published baseline and edit lock. | Current labels can be semantically confusing; shared control is foundational. | High | P0 | R005,R069,R078 | Generic product | Visible | Version branching and retention rules | Cycle > Versions; Planning Governance | FP&A Manager
S29 | Budget Versions | Version comparison | 23 | Version-versus-version account-level differences | Keep + Modify | Show comparand selectors, absolute/% delta, filters, source, reason and drill-to-change. | Facilitates approval and accountability. | High | P0 | R005,R051,R071,R078 | Generic product | Visible | Value sign conventions and comparison dimensions | Cycle > Compare Versions | FP&A Manager
S30 | Budget Versions | Version history | 23 | Chronological version history | Merge | Use single event store across budgets, revisions, forecasts and scenarios with immutable published snapshots. | Avoids conflicting histories. | High | P0 | R005,R078 | Generic product | Visible | Immutable baseline storage design | Planning Governance > History | FP&A Controller
S31 | Approval Workflows | Central approval dashboard | 24 | Submissions by business unit and workflow stage | Keep + Modify | Create My Approvals/All Approvals filtered by entity, role, status, cycle and due date. | Gives approvers actionable work queue. | High | P0 | R008,R009,R069 | Generic product | Visible | Delegation and SLA policy | Planning Governance > My Approvals | Approver
S32 | Approval Workflows | Approve/Reject action controls | 24 | Decision buttons for pending review items | Modify | Enforce authenticated authority, SoD, mandatory rejection reason, return-for-changes and persistent decision event. | Prevents unapproved or self-approved submissions. | High | P0 | R009,R069,R078 | Generic product | Visible; backend absent | Approval thresholds and conditional routing | Planning Governance + contextual approval | Approver
S33 | Approval Workflows | Workflow definition / policy | 24 | Multiple stage patterns shown by unit | Add | Build reusable workflow configuration for budget, targets, revisions and optional advanced plans; route from object type/scope. | Existing screens imply multiple approval patterns but do not show rules definition. | High | P0 | R008,R009,R069 | Generic product | Inferred need | Define policy author, workflow migration | Planning Configuration > Workflows | FP&A Administrator
S34 | Budget Comments | Cell annotations and budget-line discussion | 26 | Amount grid with comment indicators and threads | Merge | Embed threaded comments directly against entity/account/period/version; allow mention and resolution. | Users should review and discuss without leaving context. | High | P0 | R055,R069,R078 | Generic product | Visible | Comment visibility and locking behavior | Cycle > Budget Grid > Discussion | Budget Owner
S35 | Budget Comments | Comment/action register and review log | 26–27 | Comment summary, action items and reviewer history | Keep + Modify | Retain one searchable resolution queue; filter overdue/unresolved, assigned user and plan scope. | Central oversight without duplication of entry screens. | Medium | P1 | R055,R069,R078 | Generic product | Visible | Resolution SLA and submit blocking rules | Planning Governance > Issues | FP&A Manager
S36 | NEW | Planning landing / My Work | New | Not evidenced in provided 27 pages | Add | Role-specific overview of active cycles, upcoming deadlines, drafts, submissions, exceptions and approval tasks. | Users need a single starting point. | High | P0 | R008,R009,R014,R069 | Generic product | Not evidenced in scope | Define home widgets and user access | FP&A > My Work | All personas
S37 | NEW | Budget Cycle create/manage | New | No cycle configuration UI established in provided pages | Add | Create annual budget with year, entity/department scope, owner, deadlines, model, granularity and workflow policy. | Single orchestration container for budget lifecycle. | High | P0 | R006,R008,R014,R069 | Generic product | Not evidenced in scope | Cycle settings and parallel cycle handling | Budget Planning > Cycles | FP&A Manager
S38 | NEW | Master-data mapping and input validation | New | Dimensions visible only as selections | Add | Map planning chart of accounts, centres, entities, currency and fiscal periods; validate imports and line-items. | Correct financial data is prerequisite for reliable budgets. | High | P0 | R001,R002,R003,R007,R013 | Generic product | Not evidenced in scope | Confirm ownership by existing ERP platform | Planning Configuration | FP&A Administrator
S39 | NEW | Historical actuals import & reconciliation | New | Historical values referenced; source loading not shown | Add | Support controlled CSV import for prototype/MVP and a GL adapter interface; show mapping issues and source reconciliation. | Enables credible baseline and budget-vs-actual. | High | P0 | R010,R013,R049,R077 | Generic product | Not evidenced in scope | Actuals source, refresh and cut-off rules | Planning Data > Imports | FP&A Analyst
S40 | NEW | Revenue / OpEx / workforce / CapEx model views | New | Not part of 27-page Planning & Budgeting subset | Add / Link | Provide cycle-linked planning models; reuse existing Revenue & Sales / Cost Management when possible, avoid duplicate menus. | Coherent operating budget requires financial drivers by domain. | High | P0 | R020,R021,R022,R023,R024 | Generic product | Other Entroid areas unreviewed | Inspect existing models before deciding Build/Reuse | Budget Cycle > Models | Functional Planning Owners
S41 | NEW | Consolidation and validations workspace | New | No complete aggregation/reconciliation journey evidenced | Add | Aggregate department/entity budgets, detect missing submissions, duplicates, unmapped accounts and target breaches. | Required for approvable group plan. | High | P0 | R016,R042,R079 | Generic product | Not evidenced in scope | Level of entity consolidation/FX support | Cycle > Consolidation | FP&A Manager
S42 | NEW | Planned statements & financial reconciliation | New | Selected long-range financial tables, no complete integrated engine | Add / Link | Calculate scoped P&L, BS and CF views from plan models with reconciliation indicators and known limitations. | Completes core financial planning deliverable. | High | P0 | R025,R026,R070 | Generic product | Partial UI evidence only | Define BS/CF schedules and ownership with reporting | Financial Performance | FP&A Manager
S43 | NEW | Actual vs Budget variance workspace | New | Not established in 27-page subset | Add / Link | Compare mapped actuals with published budget by dimensions, period and account; add explanations and trace to source. | First monitoring loop after publishing. | High | P0 | R049,R055,R071 | Generic product | Other reporting area unreviewed | Check Reporting & Analysis module coverage | Financial Performance | FP&A Manager
S44 | NEW | Forecast cycle with approved budget baseline | New | Reforecast implied in Budget Revision, no distinct workflow | Add / Link | Manage latest estimate separately from budget baseline; actualised periods locked and future months forecast. | Avoids changing approved budget to match expectation. | Medium | P1 | R027,R028,R029,R031,R032 | Generic product | Not fully evidenced in scope | Forecast horizon, roll-forward and freeze policy | Forecasts & Scenarios | FP&A Manager
S45 | NEW | Scenario workspace & assumption comparison | New | Contingency screens exist, financial what-if not fully evidenced | Add / Link | Create isolated scenario branches from baseline, change drivers and compare impacts without posting to published plan. | Supports forward-looking decision making. | Medium | P1 | R043,R044,R045,R047,R048 | Generic product | Other scenarios module unreviewed | Inspect Forecasting & Scenarios before build | Forecasts & Scenarios | FP&A Manager

## 83 Requirements Trace
Requirement ID | Catalogue Category | Sub-Capability | Original Requirement / Feature Statement | Source | Client Y/N Interpretation | 27-Page UI Evidence | Recommended Wave | MVP Coverage / Scope Caveat | Linked Change IDs | Traceability Note
R001 | Master Data & Configuration | Legal Entities & Planning Units | Define legal entities, business units, cost centers, profit centers, and planning units for structured planning. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S02,S38 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R002 | Master Data & Configuration | Chart of Accounts & Planning Accounts | Configure planning chart of accounts including revenue, cost, and balance sheet accounts. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S02,S06,S10,S38 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R003 | Master Data & Configuration | Dimensions & Hierarchies | Define planning dimensions (entity, product, customer, geography, channel, project) with alternate hierarchies. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S02,S06,S38 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R004 | Master Data & Configuration | Custom / Extension Dimensions | Add user-defined dimensions (program, initiative, campaign) for granular planning views. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S22,S25 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R005 | Master Data & Configuration | Planning Versions & Scenarios | Configure multiple versions (Actual, Budget, Forecast, What-If) and scenario labels. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S03,S04,S15,S17,S28,S29,S30 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R006 | Master Data & Configuration | Planning Time Horizons & Frequency | Configure short-term, mid-term, and long-term horizons with daily/weekly/monthly/quarterly frequency. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP monthly budget cycle; daily/weekly/quarterly frequency deferred | S01,S10,S37 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R007 | Master Data & Configuration | Currencies & FX Rates | Configure planning, functional, and reporting currencies with plan FX rates. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP single currency per budget and currency fields; advanced translation deferred | S38 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R008 | Master Data & Configuration | Planning Calendar & Workflow | Configure planning calendar with milestones, gates, and stakeholder responsibilities. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S08,S31,S33,S36,S37 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R009 | Master Data & Configuration | Security & Data Access | Role-based access by entity, dimension, form, and version with segregation of duties. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S08,S24,S31,S32,S33,S36 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R010 | Data Integration & Sourcing | Actuals from GL / Universal Journal | Real-time ingestion of actuals from GL for variance analysis at plan-account level. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | MVP source-controlled upload and mapping; realtime GL integration deferred | S39 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R011 | Data Integration & Sourcing | Sub-Ledger Actuals | Ingest actuals from AR, AP, FA, HCM, and other sub-ledgers for granular analysis. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R012 | Data Integration & Sourcing | Operational Data Ingestion | Ingest operational drivers (volumes, headcount, prices, mix) from SD, MM, PP, HR. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R013 | Data Integration & Sourcing | Manual Data Entry & Uploads | Support Excel/CSV uploads and manual entry via web forms for supplementary data. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S11,S38,S39 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R014 | Budgeting | Annual Operating Budget | Prepare annual operating budget for revenue, cost, and capital expenditure with top-down and bottom-up methods. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S05,S09,S10,S11,S36,S37 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R015 | Budgeting | Top-Down Budgeting | Cascade high-level targets from executive management to departments with allocation logic. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S05,S06,S07 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R016 | Budgeting | Bottom-Up Budgeting | Aggregate detailed departmental budgets into a consolidated group budget. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S07,S09,S11,S41 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R017 | Budgeting | Zero-Based Budgeting (ZBB) | Support zero-based budgeting with cost justification from a zero base each cycle. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S12,S13,S14 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R018 | Budgeting | Activity-Based Budgeting (ABB) | Plan costs based on activities and drivers (ABC-linked) for accurate cost planning. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R019 | Budgeting | Driver-Based Budgeting | Plan revenue and cost using operational drivers (volume, price, mix, DSO, DPO). | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP basic financial drivers; full driver engine later | S03,S13 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R020 | Budgeting | Capital Expenditure (CapEx) Planning | Plan CapEx projects with lifecycle costs, depreciation, and business case ROI. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP basic CapEx lines/depreciation assumptions; full lifecycle+ROI later | S40 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R021 | Budgeting | OpEx / Cost Planning | Plan operating expenses by department, cost element, and cost driver. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S09,S10,S40 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R022 | Budgeting | Workforce / Headcount Planning | Plan headcount, salaries, benefits, and payroll-related costs with position-level detail. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP headcount/payroll aggregate; position-level modelling later | S40 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R023 | Budgeting | Sales & Revenue Planning | Plan sales revenue by customer, product, region, and channel with pricing simulation. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP basic revenue plan; full customer/channel pricing simulations later | S10,S40 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R024 | Budgeting | COGS & Margin Planning | Plan cost of goods sold and margin by product with material, labor, and overhead split. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP high-level margin models; detailed material/labour allocations later | S40 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R025 | Budgeting | Cash Flow Budgeting | Prepare cash flow budget aligned with P&L and BS plans. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP scoped cash flow budget; complex treasury projections later | S42 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R026 | Budgeting | Balance Sheet Planning | Plan balance sheet items (AR, AP, inventory, borrowings, equity) with roll-forward logic. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | MVP scoped BS roll-forwards; full ledger-specific logic later | S42 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R027 | Forecasting | Rolling Forecast | Continuous rolling forecast (12/18/24 months) with monthly refresh cycles. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S15,S44 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R028 | Forecasting | Quarterly / Interim Forecasts | Prepare quarterly and interim forecasts with reforecast triggers. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S15,S44 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R029 | Forecasting | Latest Estimate (LE) | Maintain latest estimate combining year-to-date actuals with forward-looking projections. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S16,S44 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R030 | Forecasting | Predictive / AI Forecasting | AI/ML-based predictive forecasts using historical data and external signals. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R031 | Forecasting | Trend-Based Forecasting | Statistical forecasting using trend, seasonality, and cyclical patterns. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S44 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R032 | Forecasting | Driver-Based Forecasting | Forecast based on operational and macroeconomic drivers with sensitivity to changes. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S44 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R033 | Forecasting | Hybrid Forecasting Methods | Combine multiple methods (statistical + driver + manual override) for higher accuracy. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R034 | Forecasting | Forecast Accuracy Tracking | Track forecast accuracy (MAPE, bias, hit rate) by line item, entity, and horizon. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R035 | Forecasting | Continuous Planning | Move from periodic to continuous planning with always-on updates. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R036 | Integrated Financial & Operational Planning | Sales & Operations Planning (S&OP) | Integrated S&OP linking demand, supply, and financial plans in a single process. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R037 | Integrated Financial & Operational Planning | Integrated Business Planning (IBP) | Link financial plan with operational plans (production, supply chain, HR, IT). | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S22,S23 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R038 | Integrated Financial & Operational Planning | HR / Workforce Planning Integration | Integrate workforce planning with financial planning for accurate people-cost projection. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R039 | Integrated Financial & Operational Planning | Supply Chain Planning Integration | Link demand plan, supply plan, and inventory plan to financial impact. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R040 | Integrated Financial & Operational Planning | CapEx & Project Planning Integration | Integrate capital and project plans with financial statements and cash flow. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S25,S26 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R041 | Integrated Financial & Operational Planning | Marketing & Campaign Planning Integration | Integrate marketing/campaign spend and expected revenue impact into financials. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S25 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R042 | Integrated Financial & Operational Planning | Cross-Functional Reconciliation | Reconcile financial and operational plans with variance identification and resolution. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP essential reconciliations only; cross-functional planning later | S23,S26,S41 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R043 | Scenario & What-If Analysis | Scenario Modeling | Model best-case, worst-case, and base-case scenarios with driver-based assumptions. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S19,S20,S45 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R044 | Scenario & What-If Analysis | What-If Simulation | Run instant what-if simulations with immediate impact on P&L, BS, and cash flow. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S20,S45 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R045 | Scenario & What-If Analysis | Sensitivity Analysis | Analyze sensitivity of KPIs to changes in key drivers (price, volume, FX, rates). | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S45 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R046 | Scenario & What-If Analysis | Stress Testing | Stress test plans against adverse scenarios (recession, FX shock, supply disruption). | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S19,S20 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R047 | Scenario & What-If Analysis | Scenario Comparison & Ranking | Compare multiple scenarios side-by-side with ranking by KPI outcomes. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S45 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R048 | Scenario & What-If Analysis | Assumption Management | Central library of assumptions (rates, drivers, growth) with governance and versioning. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S03,S19,S45 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R049 | Variance & Performance Analysis | Actual vs. Budget Variance | Compare actuals to budget by account, entity, cost center, and time period. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S39,S43 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R050 | Variance & Performance Analysis | Actual vs. Forecast Variance | Compare actuals to latest forecast with root-cause drill-down. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S16 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R051 | Variance & Performance Analysis | Budget vs. Forecast Variance | Analyze variance between original budget and latest forecast. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S15,S16,S29 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R052 | Variance & Performance Analysis | Price / Volume / Mix Variance | Decompose revenue and cost variance into price, volume, and mix components. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R053 | Variance & Performance Analysis | FX Impact Analysis | Isolate FX impact on financial results with constant-currency views. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R054 | Variance & Performance Analysis | Root-Cause Drill-Down | Drill from summarized variances to source transactions and journal entries. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R055 | Variance & Performance Analysis | Commentary & Explanations | Attach comments, explanations, and action items to variance items. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S34,S35,S43 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R056 | Variance & Performance Analysis | Trend & Rolling Variance Analysis | Analyze variance trends over rolling periods to identify systemic issues. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R057 | Allocations & Modeling | Cost Allocations | Model and allocate shared costs (IT, HR, corporate) across business units using drivers. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R058 | Allocations & Modeling | Revenue Allocations | Allocate revenue and margins across products, customers, or channels. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R059 | Allocations & Modeling | Driver-Based Allocations | Configurable driver-based allocation rules with traceability. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S07 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R060 | Allocations & Modeling | Multi-Step Waterfall Allocations | Multi-step cascading allocations from cost pool to activities to receivers. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S14 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R061 | Allocations & Modeling | Transfer Pricing Modeling | Model internal transfer prices for operational transfer pricing purposes. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R062 | Allocations & Modeling | Financial Modeling Layer | Custom financial modeling layer for complex, non-standard calculations. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R063 | KPIs & Performance Management | Financial KPIs (Revenue, EBITDA, ROI, Cash) | Configurable financial KPIs including revenue growth, margins, EBITDA, ROI, cash flow. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S01,S04,S22,S25,S26 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R064 | KPIs & Performance Management | Operational KPIs | Operational KPIs (volume, utilization, DSO, DPO, DIO, headcount productivity). | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R065 | KPIs & Performance Management | Strategic KPIs & Balanced Scorecard | Balanced scorecard KPIs across financial, customer, process, and learning perspectives. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | S01,S13 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R066 | KPIs & Performance Management | Target Setting & Cascading | Set strategic targets and cascade to operational KPIs across the organization. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S05,S06,S07 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R067 | KPIs & Performance Management | KPI Trends & Benchmarking | Track KPI trends and benchmark against internal and industry standards. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S04,S26 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R068 | KPIs & Performance Management | Alerts & Threshold Monitoring | Configurable alerts on KPI threshold breaches with escalation workflows. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R069 | Workflow & Collaboration | Planning Governance Framework | Configure multi-level workflows for plan submission, review, approval, task tracking, ownership, due dates, dependencies, notifications, reminders, and escalations. Support collaborative planning through comments, annotations, concurrent updates, version locking, access control, and audit trail for approved plans. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP configurable submission and approval; concurrent real-time editing and advanced escalations later | S08,S09,S11,S12,S14,S17,S18,S21,S27,S28,S31,S32,S33,S34,S35,S36,S37 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R070 | Reporting & Analytics | Standard Financial Statements | Auto-generate planned P&L, Balance Sheet, and Cash Flow with drill-down. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP scoped planned P&L, BS and CF; complete drill-down/report engine later | S01,S20,S23,S42 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R071 | Reporting & Analytics | Variance Reports | Standard variance reports (Actual vs Budget, Actual vs Forecast) with dimensions and filters. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | S16,S29,S43 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R072 | Reporting & Analytics | Executive Dashboards | Executive-level dashboards with financial KPIs, trends, and drill-down. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P0 — Core MVP | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R073 | Reporting & Analytics | Management Reports & Report Books | Curated report books for management review meetings and board packs. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R074 | Reporting & Analytics | Ad-Hoc & Multi-Dimensional Analytics | Multi-dimensional slice-and-dice with drill-through to source transactions. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | S02 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R075 | Reporting & Analytics | Real-Time Reporting | Real-time reporting on actuals, plan, and forecast with instant refresh. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R076 | AI & Advanced Analytics | Intelligent Analytics Framework | Leverage AI and machine learning to generate planning insights, forecasts, anomaly detection, forecast bias analysis, and optimization recommendations. Support conversational planning, what-if analysis, narrative generation, and automatic selection of the most suitable forecasting model for each planning line item. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R077 | Integration Points | Enterprise Integration Ecosystem | Integrated enterprise planning connectivity with real-time GL actuals, plan-derived postings, and seamless integration across CO, HR, sales, supply chain, projects, treasury, tax, and group reporting for consolidated planning and disclosures. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P2 — Advanced / Optional | Future enterprise integration ecosystem; MVP interface/readiness only | S39 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R078 | Audit Trail & Controls | Full Change History | Planning governance, auditability, and version control with complete audit trails, workflow tracking, source-to-plan traceability, approval and submission history, immutable version management, and impact analysis of assumption and driver changes. | Generic | Y/N intentionally ignored | Relevant UI concept shown; backend unimplemented | P0 — Core MVP | MVP authoritative change events and immutable published versions; extended impact analytics later | S04,S08,S15,S17,S18,S21,S24,S27,S28,S29,S30,S32,S34,S35 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R079 | Additional Attributes | Multi-Entity / Multi-Country Support and FX translation | Multi-entity and multi-currency planning with consolidated planning across entities, countries, and time zones, including local, group, and reporting currency views with automated FX translation. | Generic | Y/N intentionally ignored | Future-state addition / other ERP area not assessed | P1 — Expansion | MVP entity-level aggregation; full multi-currency, countries and FX translation later | S41 | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R080 | Additional Attributes | Multi-GAAP / Parallel Ledgers | Support plans under IFRS, local GAAP, and management views from a single data source. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R081 | Additional Attributes | Multi-Language & Localization | Multi-language UI and localized formats for global rollouts. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R082 | Additional Attributes | Scalability for High-Volume Data | In-memory processing to handle high-volume planning data with real-time calculations. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P2 — Advanced / Optional | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence
R083 | Additional Attributes | Self-Service for Business Users | Business-user-friendly configuration, form design, and calculation authoring without heavy IT dependency. | Generic | Y/N intentionally ignored | No direct evidence in 27-page subset | P1 — Expansion | Implement the stated capability in the wave shown, subject to acceptance criteria | No direct mapped row | Evaluate across wider FP&A ERP; outside PDF is not proof of absence

## Proposed Navigation
Destination | Function / User Journey | Delivery | Source Mapping
FP&A / My Work | Role-scoped assigned budgets, approvals, exceptions, deadlines | P0 | New dashboard; links to contextual task
Budget Planning / Budget Cycles | Create, open, monitor annual planning cycles | P0 | New orchestration object
Budget Cycle / Overview | Status, entities, departments, targets, deadlines and issues | P0 | New hub, reuse target/dept components
Budget Cycle / Targets | Top-down target allocation and context approval | P0 | Budget Targets pp.4–6
Budget Cycle / Department Inputs | Editable account/month inputs with models and submission | P0 | Department Budgets p.7
Budget Cycle / Consolidation | Aggregated financial lines, exceptions and mapped models | P0 | New
Budget Cycle / Approvals & Versions | Approvals, snapshot compare, published baseline | P0 | Versions p.23; Workflow p.24
Financial Performance | P&L/BS/CF, actual-to-plan variances, dashboards | P0–P1 | Reuse Reporting & Analysis if present
Forecasts & Scenarios | Latest estimate, rolling forecasts, what-if plans | P1 | Reuse existing top-level forecasting modules
Advanced Planning | Long-range, ZBB, initiatives, contingency, M&A | P2 | Reposition pp.1–4,8–10,13–21
Planning Governance | My Approvals, unresolved comments, audit history | P0–P1 | Shared services from pp.23–27
Planning Configuration | Account mapping, permissions, calendars, drivers, templates | P0 | Reuse platform setup and common ERP masters

## Workflows and Rules
Step | Stage | Primary Actions | Business Outputs | Critical Rules | Lead Persona | Catalogue IDs | Wave
W01 | Foundation & accounts | Set up planning entities, accounts, periods, dimensions, user scope, currencies | Master data + period/currency policies | Blocked if unmapped required accounts | Administrator | R001–R009 | P0
W02 | Open budget cycle | Create annual plan with business scope, phases, deadlines, owners and models | Budget cycle + draft version | Cannot activate if planning scope invalid | FP&A Manager | R006,R008,R014,R069 | P0
W03 | Actuals & targets | Import prior actuals, capture assumptions, cascade departmental targets | Actuals dataset; targets | Reconcile import totals; no over-allocation; valid source | FP&A Analyst | R010,R013,R015,R066 | P0
W04 | Prepare department budgets | Enter by account, department, period plus revenue, cost and resource models | Draft department plans | Account access, mandatory fields, cross-account checks | Budget Owner | R014,R016,R020–R024 | P0
W05 | Validate & consolidate | Resolve missing submissions, warnings, double counts and aggregations | Consolidated draft financial plan | Control totals, currency rules, funding references | FP&A Manager | R016,R042,R079 | P0
W06 | Review & approve | Submit, return for changes, approve, comment and record decision | Approved submitted snapshot | Authority matrix, SoD, comments, concurrency/version check | Approver | R009,R069,R078 | P0
W07 | Publish baseline | Create immutable approved version, update read-only comparison baseline | Published annual budget | Publish rights, ledger snapshot, no mutation of prior published | FP&A Manager | R005,R078 | P0
W08 | Monitor actuals | Load monthly actuals and analyse actual versus published budget | Variance and management outputs | Account mapping/cutoff, sign logic, reconcile to actual source | FP&A Manager | R049,R055,R070,R071 | P0
W09 | Forecast and revise | Build latest estimate using YTD actuals + future; separately request formal budget amendment | Forecast version or revised budget | No baseline overwrite; independent approval rules | FP&A Manager | R027–R029,R051,R078 | P1
W10 | Advanced methods | Optional ZBB, initiative planning, M&A and contingencies | Linked planning drivers and investment proposals | No double posting; optional activation gates | Business Sponsor | R017,R037,R040,R043 | P2

## Decisions and Questions
ID | Status | Decision / Question | Implication | Basis | Next Action
D01 | Approved | Workflow-first role-based navigation | Do not mimic all 11 existing items as primary destinations | User decision | No blocker
D02 | Approved | Advanced methods are optional and configurable | ZBB, M&A, contingencies, initiatives and LRP remain extensible | User decision | Need enablement/permissions details later
D03 | Approved | Core complete budgeting MVP before advanced breadth | P0 then P1/P2 | User decision | Agree acceptance tests
D04 | Proposed | Budget revision differs from forecast | Revised approved budget requires separate controlled baseline | Domain model | Confirm client accounting policy
D05 | Proposed | Shared plan/version engine | Budget, forecast and scenario do not duplicate fact models | Architecture recommendation | Tech design required
D06 | Proposed | Approval service shared across all plan objects | Workflow definitions and role scopes configurable | Architecture recommendation | Set SoD/threshold policy
D07 | Proposed | Department budgets + top-down targets are core | ZBB alternative method is optional | Architecture recommendation | Mixed-method policy
D08 | Proposed | Planned P&L/BS/CF supported at basic scope | Not equivalent to unrestricted statement engine | Domain recommendation | Scope BS and cash-flow schedules
D09 | Open | Financial models already under Revenue/Cost/Forecast menus | Do not duplicate current top-level ERP modules | Evidence limitation | Review other modules later
D10 | Open | Actuals upload vs live GL integration in MVP | CSV/controlled import plus adapter interface suggested | Technology tradeoff | Confirm accounting integration readiness
D11 | Open | Multi-entity and currency baseline | Entity-level data + basic aggregation P0; advanced FX/elimination later | Scope decision | Confirm supported customer requirements
D12 | Open | Budget approval thresholds and hierarchy | Use configurable rules rather than hardcoded CFO stages | Business policy | Collect org approval examples